## Read 1st
Developed by Cliff Johnson, revised 11/16/2003
Abreviation
AI | Analog Inputs: enter the total for the system
AO | Analog Outputs: enter the total for the system
DI | Digital Inputs: enter the total for the system
DO | Digital Outputs: enter the total for the system
PID | Control or function blocks: Enter the total number of estimated controllers (TIC, PIC, FIC, ect.)
DH | Data Highways like DH+: Enter the estimated total network runs
E1 | Ethernet, LAN or Server - Client Communcation: Enter the total number of network runs
ALA | Alarms Blocks: enter the total number of alarms not configured in PID blocks
OIS | Operator Interface Stations or Workstation: Enter the total number of stations
P&IDs | This is for estimating the number of Process Screens: Enter the total P&ID diagrams
ODC | Overhead Direct Costs
~ | Do not attempt to enter any information this color is auto calculated
You are to enter quantities in the grayed cells after unit hours & costs are corrected
Unless the quantity shown that has been auto calculated needs adjustment
If it is not a grayed cell and does not contain a ~, then you can adjust the quantity
Notes: | 1. Be sure all totals = 0 before you begin entering estimate (gray cells)
2. If equipment or other costs need to be modified you must "Unprotect" the worksheet first.equipment cost are based on high average and should be changed actual if action cost are known

## est form
| Integration Estimating Form | Sumary is rows 40-45 and prints on page 1 | [9 empty] | By:
FOR: | [11 empty] | DATE:
|  | See Sheet 2 for abreviations and help | [6 empty] | Fill in grayed cells for estimate
QTY | Task | AI | AO | DI | DO | PID | DH | E1 | ALA | OIS | Unit $ | P&Ids
| Enter I/O here, automatic cost calc>> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See eguip | 0 | << Enter
Fill in grayed cells only
| PLC Development (Hours) | Do not change cells this color is calculation
Fill in grayed cells only |  | Change cells for unit man-hours or device cost | [10 empty] | Hours
~ | RLL development Dwgs | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 |  |  | 0.2 |  |  |  | 0
~ | PLC Database development | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 |  |  |  | 2 |  |  | 0
~ | PLC Programming using PC software | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 |  |  |  | 4 |  |  | 0
~ | Troubleshooting programming | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 |  |  | 0.2 |  |  |  | 0
~ | Troubleshooting Hardware | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 2 | 1 |  | 2 |  |  | 0
~ | RLL Documentation | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 |  |  |  | 0
~ | Procurement, Documnentation | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 4 |  |  | 0
[12 empty] | subtotal hours for PLC | 0
SCADA development (Hours)
Fill in grayed cells only | [12 empty] | Hours
~ | HMI Loading and System Configuration | [8 empty] | 4 |  |  | 0
0 | Screen development based on P&ID s | [10 empty] | 4 | 0
~ | Screen Development for alarms | [7 empty] | 0.5 |  |  |  | 0
0 | Trend Screens (4 per screen) | [10 empty] | 1.5 | 0
0 | Real Time Report Screens | [10 empty] | 1.5 | 0
0 | Historical Report Screens | [10 empty] | 3 | 0
~ | Control Station Screens (8/screen) | [11 empty] | 0
~ | Database development | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 |  |  | 0.1 |  |  |  | 0
~ | I/O Driver configuration | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 |  |  |  | 4 |  |  | 0
~ | Test & Troubleshoot Driver | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [6 empty] | 0
~ | Client Review and update all screens | [11 empty] | 0
~ | Setup Data and Communication Hwy | [5 empty] | 4 | 4 |  | 2 |  |  | 0
~ | Comm Highway Troubleshooting | [5 empty] | 4 | 2 |  | 2 |  |  | 0
~ | Load & Configure PC Anywhere | [8 empty] | 4 |  |  | 0
~ | Procurement, Documnentation | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 4 |  |  | 0
[12 empty] | subtotal hours for SCADA | 0
[12 empty] | Total specialist hours | 0
| Summary prints this page 1 or 2 | [7 empty] | *Total labor cost |  |  |  | 0
[9 empty] | Total ODC cost |  |  |  | 0
| *Labor cost is with NO markup | [6 empty] | Total equipment cost |  |  |  |  | 0
|  | Date: | [5 empty] | Approved By
| Panel Fab, Assembly & Wire | (calc in dollars)
Fill in grayed cells only | [12 empty] | Dollars
0 | Fabrication (2 Dr Flr Mtd 6'x5'x2') | [9 empty] | 1600 |  | 0
~ | Assemble and wire | 15 | 15 | 12 | 12 | [7 empty] | 0
~ | terminals | 6 | 6 | 5 | 5 | [7 empty] | 0
~ | Continuity check | 1.2 | 1.2 | 1.2 | 1.2 | [7 empty] | 0
~ | Transmitter Power Supplies | 12.5 | [10 empty] | 0
[12 empty] | Total cost of panels (does not include PLC or SCADA equipment) | 0
` | PLC equipment cost | (calc in dollars)
Fill in grayed cells only
~ | Racks, Cable and Hardware | 15 | 15 | 10 | 10 | [7 empty] | 0
0 | Remote Racks | [9 empty] | 1200 |  | 0
0 | Processors | [9 empty] | 2500 |  | 0
~ | I/O cards | 125 | 175 | 20 | 40 | [7 empty] | 0
0 | PLC to Host Interface Card | [9 empty] | 1701 |  | 0
0 | Rack to host interface card | [9 empty] | 1200 |  | 0
0 | Programming software | [9 empty] | 800 |  | 0
0 | Redundancy kit | [9 empty] | 5000 |  | 0
0 | Power Supplies | [9 empty] | 500 |  | 0
| Prices Based on Modicon Quantum | [10 empty] | PLC equipment & Software cost | 0
` | SCADA Equipment cost | (calc in dollars)
Fill in grayed cells only
~ | Industrial Personal Computer(IPC) | [8 empty] | 3750 |  |  | 0
~ | Data Highway Interface | [8 empty] | 250 |  |  | 0
~ | Ethernet Highway | [8 empty] | 125 |  |  | 0
~ | SCADA Software & Drivers | [8 empty] | 11200 |  |  | 0
~ | Operating Software | [8 empty] | 450 |  |  | 0
~ | Computer cable and hardware | [8 empty] | 500 |  |  | 0
~ | Microsoft Office 10 | [8 empty] | 525 |  |  | 0
| ` | [10 empty] | SCADA equipment & Software cost | 0
` | Overhead Direct Costs | (calc in dollars)
Fill in grayed cells only
0 | Trips to site for Installation & Checkout | [9 empty] | 800 |  | 0
0 | Auto Rental per day | [9 empty] | 55 |  | 0
0 | Auto Private | [9 empty] | 0.32 |  | 0
0 | Motel & Meal cost (enter Days) | [9 empty] | 115 |  | 0
0 | Telephone / postage (based on total hours) | [9 empty] | 5 |  | 0
0 | CADD Cost (per dwg) | [9 empty] | 12 |  | 0
0 | Reproduction | [9 empty] | 500 |  | 0
0 | Mobile PC Cost based on weeks in field | [9 empty] | 125 |  | 0
0 | Desktop PC Cost based on weeks | [9 empty] | 75 |  | 0
[12 empty] | ODC cost | 0